## Inventory
ID | Category | Item | Qty | Unit | Brand / Model | Color / Finish | Product Link | Manual / Install PDF | Location | Warranty | Subcontractor / Supplier | Maintenance Notes | Status | Source | Conflict / Note
G-01 | General | Post-frame storage building, 24'x36'x12', 864 SF, Type V-B | 1 | ea | Graber Post Buildings post-frame (contract #77537) | See rows below | https://www.graberpost.com | https://www.graberpost.com/wp-content/uploads/2020/12/custom-building-options-from-graber-post-building.pdf | Martinsville Elementary, 3555 Centennial Rd, Martinsville IN 46151 (Conap/ComCheck) | Graber: correct deficiencies; claims in writing within 30 days and actions within 1 yr of Substantial Completion (contract T&C 17, 24, 28). Substantial Completion date TO BE FIELD VERIFIED | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | Annual walk-around: fasteners, trim, grade sloping away from posts. | CONFIRMED | Graber contract #77537 (signed 8/18/2026); Conap DBT; ComCheck | Drawing title block zip reads 47151; Conap/ComCheck read 46151. Occupancy S-1 (A100 8/19, Conap) vs U (A100 in Full Plan Set).
G-02 | General | Site location - building corners (State Plane coords, pts 1112/1113) and FFE 677.50 | 1 | ea | DLZ Indiana civil set | - |  |  | Pt 1112 E1540703.124 N3160707.964; pt 1113 E1540727.249 N3160744.089 ("POLE BARN"); FFE 677.50 (C3.6) | - | DLZ Indiana, LLC (civil) | Keep grade per C3.6; do not pile material against siding. | CONFIRMED | DLZ civil set C2.6/C2.9/C3.6 (in Full Plan Set / State Submittal) | Viewer site.json says no site plan exists - civil set does locate it (viewer not changed).
G-03 | General | IDHS Construction Design Release filing - DHS project 463497 | 1 | ea | State Form 37318 | - | https://www.in.gov/dhs/ |  | Owner records | - | DB Tarr & Co. (Daniel B. Tarr, PE10100918) | Keep release letter with this packet. Release letter itself not on file - TO BE FIELD VERIFIED | CONFIRMED | Filing Receipt; Conap DBT
F-01 | Foundation | Laminated posts, 3-ply 2x6 nail-lam columns, 8' o.c. eave & endwall | 16 | ea | Graber 3-ply 2x6 nail-lam (species/treatment not stated) | - | https://www.graberpost.com |  | Perimeter, S100 tags P1 | Graber workmanship per G-01 | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) / labor subcontractor (name TO BE FIELD VERIFIED) | Inspect post bases at grade for rot/damage each spring; keep soil/mulch below skirtboard. | ASSUMED | Graber contract #77537 (signed 8/18/2026); S100 Foundation (8/19/2026) | Qty 16 counted from 8' spacing; S100 P1 tags TO BE FIELD VERIFIED.
F-02 | Foundation | Precast concrete cookie (footing pad) under each post | 16 | ea | Precast | - |  |  | Bottom of each post hole | - | Labor subcontractor (TO BE FIELD VERIFIED) | None (buried). | ASSUMED | Graber contract #77537 (signed 8/18/2026); S100 Foundation (8/19/2026) | Contract 15" cookie; S100 detail 16". Qty follows F-01.
F-03 | Foundation | Post-hole concrete collar + (2) #5 x 15" rebar per post | 16 | ea | Contract: 80# Sackrete; S100: 160# Quikcrete | - | https://www.quikrete.com |  | Each post hole | - | Labor subcontractor (TO BE FIELD VERIFIED) | None (buried). | ASSUMED | Graber contract #77537 (signed 8/18/2026); S100 Foundation (8/19/2026) | Bag weight/brand conflict 80# Sackrete vs 160# Quikcrete.
F-04 | Concrete | Slab-on-grade 24x36, 4000 psi, 4 mil vapor retarder, WWF | 1 | ea | Ready-mix (supplier TO BE FIELD VERIFIED) | Plain concrete |  |  | Building interior | - | Concrete subcontractor (TO BE FIELD VERIFIED) | Seal/clean as needed; patch cracks; no drains in floor (Floor Drains: None). | ASSUMED | Graber contract #77537 (signed 8/18/2026); S100 Foundation (8/19/2026) | Thickness: contract 6" vs S100 4". WWF note W1.9 vs detail W2.9. Fine aggregate/rock base: contract 40 ton.
F-05 | Concrete | Exterior aprons 12x5 (2) and 5x5 (1) | 3 | ea | Ready-mix | Plain concrete |  |  | At overhead doors 100B/100C and walk door 100A | - | Concrete subcontractor (TO BE FIELD VERIFIED) | Keep joints sealed; watch for undermining at edges. | ASSUMED | Graber contract #77537 (signed 8/18/2026) | Sizes confirmed in contract; locations ASSUMED (viewer). Thickness per S100 ext. slab section TO BE FIELD VERIFIED.
F-06 | Concrete | Perimeter insulation 2' of 2" Styrofoam around edge of building | 1 | lot | Styrofoam (brand TO BE FIELD VERIFIED) | - |  |  | Slab perimeter | - | Concrete subcontractor | None (buried). | CONFIRMED | Graber contract #77537 (signed 8/18/2026)
F-07 | Concrete | Concrete maintenance strip around building (civil) | 1 | lot | DLZ civil key 21 | - |  |  | Around building, pts 1104-1111 (C2.9) | - | Site contractor (TO BE FIELD VERIFIED) | Keep clear; check for settlement. | TO BE FIELD VERIFIED | DLZ civil set C2.6/C2.9/C3.6 (in Full Plan Set / State Submittal) | Shown on civil set; not in Graber scope. Built?
S-01 | Structure | Pre-engineered wood roof trusses, 24' span @ 48" o.c., 4/12 gable, 1' overhang; DL 8 / SL 20 / LL 20 psf | 10 | ea | Truss maker TO BE FIELD VERIFIED (A100: member sizing by others) | - |  | Truss drawings - not on file (TO BE FIELD VERIFIED) | Roof framing, bearing on double 2x12 headers | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) (truss supplier TO BE FIELD VERIFIED) | Never hang loads from trusses without truss engineer approval; inspect bracing. | ASSUMED | Graber contract #77537 (signed 8/18/2026); A100 Floor Plan/Life Safety/Sections (8/19/2026) | CONFLICT: contract also lists "Truss Type: Flat" while roof is "Gable, 4/12 Pitch"; viewer models 4/12. Flagged, not changed. Qty 10 = 36'/4'+1 ASSUMED.
S-02 | Structure | SYP 2x12 double truss supports / continuous header | 2 | run | Southern Yellow Pine 2x12 (double) | - |  |  | Both eave walls at truss bearing | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | Inspect connections annually. | CONFIRMED | Graber contract #77537 (signed 8/18/2026); A100 Floor Plan/Life Safety/Sections (8/19/2026) | A100: "Truss Bears @ 10'-0" A.F.F." note vs ceiling height 12' and elevations "Truss Bearing 12'-0"" - TO BE FIELD VERIFIED.
S-03 | Structure | Roof purlins, spruce 2x4 @ 2' o.c. | 1 | lot | Spruce 2x4 | - |  |  | Top of trusses | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | - | CONFIRMED | Graber contract #77537 (signed 8/18/2026)
S-04 | Structure | Wall girts / nailers, spruce 2x4 | 1 | lot | Spruce 2x4 | - |  |  | Walls | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | - | ASSUMED | Graber contract #77537 (signed 8/18/2026); A100 Floor Plan/Life Safety/Sections (8/19/2026) | Spacing conflict: contract 2' o.c.; A100 section "2x4 Nailers @ 16" o/c".
S-05 | Structure | Skirtboard, 2 rows 2x6 tongue & groove | 1 | lot | 2x6 T&G (treatment TO BE FIELD VERIFIED) | - |  |  | Base of walls | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | Keep grade/soil off skirtboard. | CONFIRMED | Graber contract #77537 (signed 8/18/2026)
S-06 | Structure | Fascia gutterboard 2x6 and 2x6 fly rafters | 1 | lot | 2x6 | - |  |  | Eaves and gables | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | - | CONFIRMED | A100 Floor Plan/Life Safety/Sections (8/19/2026)
E-01 | Roof | Roof panels G-Rib 40-yr 29 ga | 1 | lot | Graber Post G-Rib (Ag Panel), 36" coverage, 3/4" rib | GPB Clay (ASSUMED per viewer/Reed 9/9/26; contract: colors to be determined) | https://www.graberpost.com/building-supplies/ag-panel | https://www.dutchtech.com/installation-instructions/ | Roof | Panel paint "40 Yr" per product name; GPB written terms TO BE FIELD VERIFIED | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | Spring/fall: check screws & washers, clear debris, look for scratches/rust; do not walk ribs carelessly. | ASSUMED | Graber contract #77537 (signed 8/18/2026); Renderings viewer v3 notes (cite Reed Tarr email 9/9/2026 fwd DLZ 9/8/2026; that email is not in the dbt@ inbox) | Color ASSUMED.
E-02 | Roof | Therma-Guard condensation/radiant barrier under roof panels | 1 | lot | Therma-Guard (DutchTech) | Reflective | https://www.dutchtech.com | https://www.dutchtech.com/installation-instructions/ | Under roof panels on purlins | Manufacturer terms TO BE FIELD VERIFIED | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | Report drips/tears; no insulation otherwise ("No insulation included"). | CONFIRMED | Graber contract #77537 (signed 8/18/2026)
E-03 | Roof | Ridge cap G-Rib 14" w/ vented roll | 1 | lot | Graber G-Rib ridge cap 14", vented closure | Clay (ASSUMED) | https://www.graberpost.com/building-supplies/ag-panel |  | Ridge | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | Check vent closure for nests/debris annually. | CONFIRMED | Graber contract #77537 (signed 8/18/2026); A100 Floor Plan/Life Safety/Sections (8/19/2026)
E-04 | Roof | Polycarbonate skylight panels (SunTuf) | 2 | ea | Palram SUNTUF | Clear (TO BE FIELD VERIFIED) | https://www.palram.com/us/product/suntuf-diy-polycarbonate-corrugated-sheets/ | https://www.palram.com/us/downloads/ | Roof, one each slope (A100 roof plan) | Palram limited warranty TO BE FIELD VERIFIED | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) (TO BE FIELD VERIFIED) | Do not step on panels; clean with mild soap; check fasteners. | TO BE FIELD VERIFIED | A100 Floor Plan/Life Safety/Sections (8/19/2026) | Shown on A100 roof plan only - not in Graber contract. Installed? qty/size TO BE FIELD VERIFIED.
E-05 | Roof | Snowguard, 1 row per side | 2 | row | Brand/model TO BE FIELD VERIFIED | - |  |  | Both roof slopes above eaves | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) guttering subcontract | Check clips after heavy snow. | CONFIRMED | Graber contract #77537 (signed 8/18/2026)
E-06 | Roof | Seamless gutters 6" incl. accessories + downspouts | 1 | lot | 6" seamless (downspouts 3x4 / qty 4 ASSUMED) | Clay (ASSUMED) |  |  | Both eaves | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) guttering subcontract (name TO BE FIELD VERIFIED) | Clean spring & fall; keep downspout outlets clear and splash-out away from posts. | ASSUMED | Graber contract #77537 (signed 8/18/2026); Renderings viewer v3 notes (cite Reed Tarr email 9/9/2026 fwd DLZ 9/8/2026; that email is not in the dbt@ inbox) | Downspout size/qty/color ASSUMED (viewer).
E-07 | Roof | Soffit G-Rib, 1' overhang all sides; trim painted standard color | 1 | lot | Graber G-Rib soffit; painted trim | Soffit/fascia Clay, trim Stone (ASSUMED) | https://www.graberpost.com/building-supplies/ag-panel |  | Eaves & gables | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | Look for loose trim after storms. | ASSUMED | Graber contract #77537 (signed 8/18/2026); Renderings viewer v3 notes (cite Reed Tarr email 9/9/2026 fwd DLZ 9/8/2026; that email is not in the dbt@ inbox) | Colors ASSUMED.
E-08 | Walls | Siding Board & Batten 10" 26 ga over house wrap and 7/16" OSB | 1 | lot | Graber Board & Batten 10" 26 ga | GPB Stone (ASSUMED) | https://www.graberpost.com |  | All exterior walls | Panel paint terms TO BE FIELD VERIFIED | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | Wash annually; touch up scratches with GPB touch-up paint. | ASSUMED | Graber contract #77537 (signed 8/18/2026); Renderings viewer v3 notes (cite Reed Tarr email 9/9/2026 fwd DLZ 9/8/2026; that email is not in the dbt@ inbox) | Color ASSUMED.
E-09 | Walls | House wrap (WRB) | 1 | lot | Brand TO BE FIELD VERIFIED | - |  |  | Behind siding | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | - | TO BE FIELD VERIFIED | Graber contract #77537 (signed 8/18/2026) | Brand not stated.
E-10 | Walls | Wainscot Affinity Stone, 3' high, with ice & water | 1 | lot | Affinity Stone Cliff Ledge (profile/color ASSUMED) | Redwood (ASSUMED) | https://www.affinitystone.com | https://www.affinitystone.com/wp-content/uploads/2024/09/INSTRUCTIONS-Affinity-Installation-Guide.pdf | Base of all walls | Manufacturer terms TO BE FIELD VERIFIED | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | Rinse; do not pressure-wash at close range; check wainscot cap. | ASSUMED | Graber contract #77537 (signed 8/18/2026); A100 Floor Plan/Life Safety/Sections (8/19/2026); Renderings viewer v3 notes (cite Reed Tarr email 9/9/2026 fwd DLZ 9/8/2026; that email is not in the dbt@ inbox) | Wainscot type confirmed; Cliff Ledge Redwood per viewer only.
E-11 | Walls | Fasteners: Woodbinder painted galvanized screws | 1 | lot | Woodbinder | Painted to match |  |  | Roof and wall panels | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | Re-tighten/replace backed-out screws. | CONFIRMED | Graber contract #77537 (signed 8/18/2026)
E-12 | Walls | UV-printed Graber Post Buildings logo | 1 | ea | Graber | Matched to building |  |  | Exterior (TO BE FIELD VERIFIED) | - | Graber Post Buildings, Inc (Montgomery, IN, 812-636-7355; preparer Darrell Wittmer) | - | TO BE FIELD VERIFIED | Graber contract #77537 (signed 8/18/2026) (T&C 31) | Installed? location TO BE FIELD VERIFIED.
D-01 | Doors | Overhead doors 100B & 100C, 10'x10', 12" standard radius track | 2 | ea | C.H.I. Overhead Doors Model 3216 (2" insulated steel sandwich) | Contract: White standard polyester; viewer: Stone (ASSUMED) | https://www.chiohd.com/architects/specifications-drawings | https://www.bartondoor.com/uploads/product-manuals/documents/CHI-COM-Doors-10_-com-instructions_5-7-2018.pdf | Front endwall (100B, 100C) | Manufacturer limited warranty TO BE FIELD VERIFIED | Door subcontractor/dealer TO BE FIELD VERIFIED | Quarterly: lube rollers/hinges/springs, check cables; springs by trained tech only. Spec sheet: https://www.chiohd.com/hubfs/Professional/Specs/Commercial/3216-Data-Sheet.pdf | ASSUMED | Graber contract #77537 (signed 8/18/2026); A100 Floor Plan/Life Safety/Sections (8/19/2026) | Windows: contract "2283 Series - 5" vs A100 "One-Row Glass". Color conflict white vs Stone.
D-02 | Doors | Overhead door operators | 2 | ea | LiftMaster (A100); model TO BE FIELD VERIFIED; contract "Operator--10'" | - | https://www.liftmaster.com | LiftMaster manual for installed model - TO BE FIELD VERIFIED | On each overhead door | Manufacturer terms TO BE FIELD VERIFIED | Door subcontractor/dealer TO BE FIELD VERIFIED | Monthly: test photo-eye and auto-reverse. | TO BE FIELD VERIFIED | A100 Floor Plan/Life Safety/Sections (8/19/2026); Graber contract #77537 (signed 8/18/2026) | Model and controls (wall station/remotes) TO BE FIELD VERIFIED.
D-03 | Doors | Walk door 100A, 3'-0"x7'-0" | 1 | ea | A100: hollow metal door w/ masonry frame; Contract: 30/70 commercial door w/ glass & hardware, white | White (contract) |  |  | Front/side wall per A100 | - | Labor subcontractor | Adjust closer/hinges; keep threshold clear. | TO BE FIELD VERIFIED | A100 Floor Plan/Life Safety/Sections (8/19/2026); Graber contract #77537 (signed 8/18/2026) | CONFLICT: 30/70 (2'6" glass commercial) vs 3'0" hollow metal (A100). Which was installed?
D-04 | Doors | Walk door hardware | 1 | ea | A100: leverset w/ SFIC keyed to school system; Contract: door knob keyed | - |  |  | Door 100A | - | School / hardware TO BE FIELD VERIFIED | Keep SFIC core records with MSD maintenance. | TO BE FIELD VERIFIED | A100 Floor Plan/Life Safety/Sections (8/19/2026); Graber contract #77537 (signed 8/18/2026) | Lever+SFIC vs keyed knob.
M-01 | Utilities | Electrical service / lighting / receptacles | 0 | - | None in Graber scope; ComCheck: "No lighting fixtures specified" | - |  |  | - | - | Owner / MSD electrical (TO BE FIELD VERIFIED) | - | TO BE FIELD VERIFIED | Graber contract #77537 (signed 8/18/2026); ComCheck | Is there power? Any fixtures installed?
M-02 | Utilities | 2" conduit for future outbuilding power, capped, pull string, flagged | 1 | ea | Per DLZ C2.6 note | - |  |  | From Electrical Room B121 (12" AFF) to approx. location near building | - | School site electrical contractor (TO BE FIELD VERIFIED) | Locate before digging; record termination on electrical record drawings. | TO BE FIELD VERIFIED | DLZ civil set C2.6/C2.9/C3.6 (in Full Plan Set / State Submittal) | Final routing/termination TO BE FIELD VERIFIED.
M-03 | Utilities | Insulation / HVAC / plumbing / floor drains | 0 | - | None (contract: no insulation, Floor Drains: None, HVAC/plumbing excluded) | - |  |  | - | - | - | ComCheck envelope shows FAILS (uninsulated, unconditioned storage). | CONFIRMED | Graber contract #77537 (signed 8/18/2026); ComCheck

## Open Questions
# | Question for Brook
1 | Trusses: contract reads "Truss Type: Flat" but the roof is "Gable, 4/12 Pitch" and the viewer models 4/12 trusses. Is "Flat" Graber's term for a standard (non-scissor) bottom chord? Please send the truss drawings.
2 | Walk door 100A: was it the 30/70 commercial glass door with keyed knob (contract) or 3'-0" hollow metal with SFIC leverset (A100)?
3 | Slab thickness and mesh: contract 6", S100 4" (and W1.9 vs W2.9 WWF). What was poured?
4 | Footings: 15" cookie + 80# Sackrete (contract) or 16" cookie + 160# Quikcrete + 2 #5 bars (S100)?
5 | Girt spacing: 2' o.c. (contract) or 16" o.c. (A100)?
6 | Truss bearing height: A100 note says 10'-0" A.F.F.; elevations say 12'-0".
7 | Colors: confirm roof/fascia/soffit Clay, siding/trim/doors Stone, Affinity Cliff Ledge Redwood (Reed 9/9/26 email is not in the dbt@ inbox), gutter color, and overhead door color (contract says white).
8 | SunTuf skylights shown on A100: installed? How many and what size/color?
9 | Overhead doors: window section (2283 Series, 5 lites vs one row), LiftMaster operator model, remotes/wall stations.
10 | Subcontractor names and phone numbers: Graber labor crew, guttering, concrete, overhead door dealer.
11 | Substantial Completion date (warranty start) and any Graber/manufacturer warranty certificates.
12 | Electrical: any power, lights or receptacles in the building? Was the 2" future-power conduit from Room B121 installed, and where does it end?
13 | Zip code: drawings say 47151, Conap/ComCheck say 46151. Occupancy U (Full Plan Set A100) vs S-1 (8/19 A100, Conap).
14 | IDHS design release letter for DHS project 463497 - please send for the file. Any Graber logo installed?
15 | No storage-building invoices or emails were found in the dbt@mail.grokbot.com inbox - are there any to add?

## Legend
CONFIRMED | Stated in a source document (contract, A100/S100, civil set, Conap/ComCheck). Conflicts between sources are listed in the last column.
ASSUMED | Inference or one source among conflicting sources; not confirmed.
TO BE FIELD VERIFIED | Not in any source document, or shown on drawings but not confirmed built. Check on site.
Pricing | None in this file. Pricing is kept in private/PRIVATE_PRICING.csv (not published).